## A
TABULATION SHEET - BARDSHAR RD IMPROVEMENTS IN MARGARETTA TWP & CITY OF SANDUSKY
Engineer's Estimate: |  | 755532
Bid Date: FEBRUARY 1, 2023 @ 9:30 a.m.
Contractor:
Item # | Quantities | Unit | Description | Unit Price | Total
ROADWAY
201 | 1 | L. S. | Clearing & Grubbing | $ | $
202 | 1123 | Ft. | Pipe Removed Under 24" | $ | $
202 | 2 | Ea. | Catch Basin Removed | $ | $
203 | 1095.5 | Cu. Yd. | Excavation | $ | $
203 | 2103 | Cu. Yd. | Embankment, As, Per Plan | $ | $
204 | 2244 | Sq. Yd. | Subgrade Compaction | $ | $
204 | 2 | Hr. | Proof Rolling, As Per Plan | $ | $
204 | 100 | Sq. Yd. | Geogrid | $ | $
254 | 965 | Sq. Yd. | Pavement Planing, Asphalt Concrete | $ | $
623 | 2 | Ea. | Monument Assembly Adjusted to Grade, As Per Plan | $ | $
623 | 1 | Ea. | Monument Assembly, As Per Plan | $ | $
Spec. | 7 | Ea. | Single Mailbox Support and Approach , As Per Plan | $ | $
Spec. | 1 | Ea. | Double Mailbox Support and Approach , As Per Plan | $ | $
Spec. | 1 | Ea. | Triple Mailbox Support and Approach , As Per Plan | $ | $
|  |  | Subtotal |  | $
EROSION CONTROL
653 | 340 | Cu. Yd. | Topsoil Furnished and Placed | $ | $
659 | 10720 | Sq. Yd. | Seeding and Mulching, Class I | $ | $
659 | 1.447 | Ton | Commercial Fertilizer | $ | $
832 | 1 | Ea. | Storm Water Pollution Prevention Plan, As Per Plan | $ | $
832 | 1 | Ea. | Storm Water Pollution Prevention Inspections | $ | $
832 | 1 | Ea. | Storm Water Pollution Prevention Inspection Software | $ | $
832 | 20000 | Ea. | Erosion Control, As Per Plan | 1 | 20000
|  |  | Subtotal |  | $
DRAINAGE
611 | 54 | Ft. | 4" Conduit, Type C, 707.45, As per plan | $ | $
611 | 40 | Ft. | 6" Conduit, Type C, 707.45, As per plan | $ | $
611 | 30 | Ft. | 8" Conduit, Type C, As per plan | $ | $
611 | 222.5 | Ft. | 12" Conduit, Type B, 706.02, As per plan | $ | $
611 | 874 | Ft. | 12" Conduit, Type C, As Per Plan | $ | $
611 | 1076 | Ft. | 12" Conduit, Type C, 706.02, As per plan | $ | $
611 | 251 | Ft. | 15" Conduit, Type C, As Per Plan | $ | $
611 | 540 | Ft. | 15" Conduit, Type C, 706.02, As per plan | $ | $
611 | 510 | Ft. | 18" Conduit, Type C, 706.02, As per plan | $ | $
611 | 16 | Ft. | 30" Conduit, Type C, 706.02, As per plan | $ | $
611 | 7 | Ea. | Catch Basin 2-2B | $ | $
611 | 16 | Ea. | Catch Basin 2-2B W/Slanted Riser | $ | $
611 | 5 | Ea. | Catch Basin 2-3 | $ | $
Spec. | 10 | Ea. | Inserta-Tee Connection, As Per Plan | $ | $
|  |  | Subtotal |  | $
PAVEMENT
301 | 275 | Cu. Yd. | Asphalt Concrete Base | $ | $
304 | 853 | Cu. Yd. | Aggregate Base | $ | $
407 | 1200 | Gal. | Tack Coat | $ | $
411 | 100 | Cu. Yd. | Stabilized Crushed Aggregate | $ | $
441 | 462 | Cu. Yd. | Asphalt Concrete Intermediate Course, Type 2, (448) | $ | $
441 | 323 | Cu. Yd. | Asphalt Concrete Surface Course, Type 1, PG64-22, (448) | $ | $
|  |  | Subtotal |  | $
PAVEMENT MARKINGS
642 | 0.56 | Mile | Centerline, Type 1 | $ | $
642 | 1.13 | Mile | Edge Line, Type 1 | $ | $
644 | 30 | Ft. | Stop Line | $ | $
|  |  | Subtotal |  | $
MAINTENANCE OF TRAFFIC
614 | 1 | L. S. | Maintaining Traffic, As Per Plan | $ | $
|  |  | Subtotal |  | $
MISCELLANEOUS
103.05 | 1 | L. S. | Premium for Contract Performance Bond and Maintenance Bond | $ | $
|  |  | Subtotal |  | $
|  |  | BASE BID CONSTRUCTION ESTIMATE OF COST |  | $
ALT BID #1 CITY OF SANDUSKY
203 | 7 | Cu. Yd. | Excavation | $ | $
203 | 7 | Cu. Yd. | Embankment, As, Per Plan | $ | $
611 | 150 | Ft. | 18" Conduit, Type C | $ | $
611 | 1 | Ea. | Catch Basin 2-3 | $ | $
611 | 1 | Ea. | Catch Basin, Adjust to Grade | $ | $
659 | 200 | Sq. Yd. | Seeding and Mulching, Class I | $ | $
659 | 0.028 | Ton | Commercial Fertilizer | $ | $
|  |  | Subtotal |  | $
|  |  | CITY OF SANDUSKY CONSTRUCTION ESTIMATE OF COST |  | $
|  |  | BASE BID + ALT #1 CONSTRUCTION ESTIMATE OF COST |  | $